## Gantt Chart
Phase / Task | Hours | Nov 2025 |  |  |  | Dec 2025 |  |  |  |  | Jan 2026 |  |  |  | Feb 2026 |  |  |  | Mar 2026 |  |  |  |  | Apr 2026 |  |  |  | May 2026
|  | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30
Phase 1: Theoretical Research | 15
Research of VLMs
RL Framework Research
State-of-the-Art Review
Phase 2: Experimentation | 45
Foundational VLM Tasks
IsaacSim Tutorials
Local Model Deployment
Basic Scene Scripting
Phase 3: Architecture Design | 60
BentoML Server Architecture
Coordinate Transformation Logic
Workflow Pipeline Design
Phase 4: Solution Development | 100
Scenarios Development
RL Policy Training
Prompt Engineering Refinement
Robot Control Integration
Phase 5: Results Evaluation & Refinement | 90
Performance Evaluation
Implementation of Improvement Techniques
Comparative Analysis
Phase 6: Documentation | 50
Final Report Writing